## Options (hidden)
Person Working the Project | Status | Priority | In Staffing center? | Product Type | Business Units
Kevin O. | 00-Coming/Waiting for Info | 🔥ON FIRE🔥 | Yes | Video | Mission Systems
John S. | 01-Creative Brief/Scoping | 1 - High | No | Video Set | Avionics
Kevin & John | 02-Estimate | 2 - Medium | ???? | Video series | RTX
TBD | 03-Outline | 3 - Low |  | Flash Development | Interior Systems
SME | 04-Script |  |  | Graphics Support | Raytheon
Jack | 05-Shoot |  |  | Video Support | Pratt & Whitney
Michelle | 06-Graphics/Audio |  |  | Traditional CBT | Power & Controls
Kevin, John, & Michelle | 06-Editing |  |  | Podcast | Advanced Structures
Exnier | 07-Review |  |  | Audio | Communications
Exnier & Kevin | 08-Delivery |  |  | Script Review | Digital Technology
Exnier & John | 09-Complete |  |  | Still Photography | Engineering & Technology
Michelle & Kevin |  |  |  | Audio Alerts | Operations
Michelle & John |  |  |  | Webinar/LiveStream | Finance
Kevin, John, & Exiner |  |  |  | PDF | Human Resources
Kevin, John, Michelle, & Exnier |  |  |  |  | GTS
Environment Health & Safety
Enterprise?
Stragetic Solutions

## Historical (hidden)
Priority | Project Name | Customer Contact | Business Unit | Cost Center/Charge Number | Project Type | Start Date | End Date | Due Date | Estimated Hours Total | Hours Burned | Hours Remaining | Status | Person Working the Project | Notes
1 - High | 🔥 Kidde Continuous Fire Detector Benchtop Thermal Test 🔥 | Kirk Thorson/Stephanie Grant |  | AP0801 6006 22674965 Av Supp CFD Test (000100136287 / 1732 / 1784) | Video | 2021-02-01 | 2021-03-12 | 2021-03-12 |  |  |  | Complete | Kevin & John | 🔥🔥🔥🔥🔥🔥🔥🔥 ON FIRE! 🔥🔥🔥🔥🔥🔥🔥🔥
1 - High | 2021 Insider Threat | Adam Russel / Maria Sacco |  | E39 | Traditional CBT | 2021-04-07 | [5 empty] | Complete | John S. | Updates for: https://crsvn/hr_cbt_projects_fy14/Insider%20Threat%20Training%202020/
1 - High | 2021 Security Briefing | Adam Russel / Maria Sacco |  | E39 | Traditional CBT | 2021-04-07 | [5 empty] | Complete | John S. | Updates for: https://crsvn/hr_cbt_projects_fy14/Security%20Briefing%202020/
1 - High | Airshow Icon Work | Maureen Vieth/Kalyani Gopalam |  | TDBMASXI CY20 Airshow AXSI-5 (000100125750 / 0562 / 0690) | Graphics Support | 2020-06-01 | 2020-09-01 |  |  |  |  | Complete | John S. | Creating vector and png icons for production.
1 - High | Avionics Engineering - Leading the way (Priborsky) | Amy Burns / Tara Kraft |  | Leigh Parker ENG CONSOLIDATION (XA0) | Video Series | 2021-02-11 | 2021-05-11 | 2021-05-11 |  |  |  | Complete | John S. | Storyboard: https://docs.google.com/document/d/1jR4UuzjCTNXlVPFdVE2AtgbTdi_f5Ck4fhOwrBmJjyY/edit
1 - High | Avionics leading the way - Rig/Lab Tours | Tara Kraft Jaime Zeets Marie McNary Paul Carter Kimberly Draker Swetha Sridharan |  | Avionics Eng Student Employee Programs (000000262627) | Video | 2020-12-03 | 2020-12-08 |  | 2025-08-16 |  |  | Complete | John S. | Hello, Thank you for showing interest and transforming the PLTW Tours into a virtual learning experience. We have a few dates that I am hoping one of which will work out for you and best fit your schedule. If you are interested in both Fall and Spring Sessions please let me know. These are the dates that are good for the schools. Fall session: December 8th 2020 (Covered by Kirkwood - no need for work on my end) Spring session: March 4th 2020 Event Details: After discussion with a few labs interested in the tour and working with the Kirkwood Workplace Learning Connection, the virtual event format is as follows: • Each lab tour will be about 20mins. • 7mins to talk through a short slide deck about the lab • 7mins for a live demo of the lab • 6mins for any Q&A from the students Feel free to combine the 7mins each from the presentation and the live demo if that works the best for your lab.
1 - High | Cabin Essence Video Project (24 videos) | Eric Dufur/Dan Burton |  | EATIS17 340 Repair Training Video Record (000100128698 / 0920 / 0922) | Video | 2019-03-11 | 2020-08-26 |  | 220 |  |  | Complete | Kevin & John | First set is finished and loaded on LMS.
1 - High | CMS Videos - SP101 | Kaitlin Johnston-Boyse |  | IO 265350 | Video series | 2021-04-07 | 2021-05-17 | 2021-05-17 |  |  |  | Complete | John S. | Editing some video content add some graphics. Usually a recorded zoom. Want's one a month.
1 - High | Essence Beverage Maker Series | Eric Dufur/Dan Burton |  | EATIS17 340 Repair Training Video Record (000100128698 / 0920 / 0922) | Video series | 2020-01-08 | 2020-12-31 |  |  |  |  | Complete | Kevin & John | These are posted on the LMS and are in use.
1 - High | Essence Espresso Maker Series | Eric Dufur/Dan Burton |  | EATIS17 340 Repair Training Video Record (000100128698 / 0920 / 0922) | Video series | 2020-01-08 | 2020-12-31 |  |  |  |  | Complete | Kevin & John | These are posted on the LMS and are in use.
1 - High | Essence Water Heater Series | Eric Dufur/Dan Burton |  | EATIS17 340 Repair Training Video Record (000100128698 / 0920 / 0922) | Video series | 2020-01-08 | 2020-12-31 |  |  |  |  | Complete | Kevin & John | These are posted on the LMS and are in use.
1 - High | MFA Demo Recording | Jeremiah Wolf |  | NWA 100143090 0060 | Video | 2021-02-18 | 2021-03-12 | 2021-03-12 | 25 |  |  | Complete | Kevin O. | Demo Video of capabilities for customer --This project is on hold for a few weeks due to a COVID scare in the lab.
1 - High | SPARC Video Story | Jiwon Moran |  | GD1511 ECP Demonstrations Labor (000100129730 / 0376 / 0620) | Video | 2020-09-01 |  | 2020-10-01 | 40 |  |  | Complete | Kevin & John | This will involve multiple cameras on a government project. Demo outside in parking lot. It's back, has sync issues - which isn't a surprise although, I thought that I fixed all of the sync problems. | Version 1 of the video is out in the video folder. \\ccanet\et\sparc_shared\restricted\Video\SPARC Demo-v1.mp4
1 - High | T44 Panels | Corinne O'Leary |  |  | Flash Development | 2020-08-03 | 2020-08-31 | 2020-10-30 | 30 |  |  | Complete | Kevin O. | Would like to wrap this project ASAP.
1 - High | WATS Moving Pictures | Doug Forret |  | C6TPS21 PL VAP Training Devices (000100142953 / 0016 / 0036) | Video | 2021-04-05 | 2021-04-09 |  |  |  |  | Complete | John S. | https://drive.google.com/drive/folders/1M87jDNIlNfWozgzJ2XliSjVXAk4FNFjs
1 - High | Z-Fab Lab - Brief Overview | Nate Oster / Nate VanderHorn |  | E30 | Video | 2020-08-20 | 2020-08-31 |  | 24 |  |  | Complete | John S. | DONE - We are looking to do a ~8-10 min video showing the z-fab lab (Lab 33A in building 107) and giving a brief overview of the parts we make. E30S-PKG
2 - Medium | Admin Thank You Video | Kaitlin Johnston-Boyse |  | 265348 FY21 MS E&T Operational Team Supt (I) | Video | 2021-04-14 | 2021-04-21 | 2021-04-16 | 6 |  |  | Complete | John S. | 30 second video. User provided footage. Edited VO audio then added screen text, music and a couple clips of b-roll.
2 - Medium | Airshow Safety Briefings | Dallas Miller/Molly Beatty |  | AIRSHOW (Y06) | Video Series | 2021-01-04 | ? |  | ? |  |  | Complete | John S. | Need to create estamate based on customer feedback. Videos are complete. May need some sort of DA approval. Also, they need to be converted using CS4 for use.
2 - Medium | Aural Warnings for AC | Christopher DeSalvo |  |  | Audio | ? | ? |  | ? |  |  | Complete | Kevin O. | Recording Audio or hiring voice talent to record Aural Warnings for flight decks
2 - Medium | Autowinder - Avionics - Burnsville videos | Melissa McLaughlin, Josh Rubin, Ed Anctil |  | KS8 | Video series | 2020-08-06 | 2020-08-20 | 2020-10-07 | 32 |  |  | Complete | John S. | Video and video series introduction complete waiting for director level approval. | https://drive.google.com/drive/folders/16zd-9eRMaqym9meqjw1dVeqAoZP0xKfy
2 - Medium | Avionics Engineering - Leading the way | Amy Burns / Tara Kraft |  | Leigh Parker ENG CONSOLIDATION (XA0) | Video Series | 2020-08-12 | ? |  | ? |  |  | Complete | John S. | Sent off to the powers that be...not sure if it's coming back, I think it's done. | https://drive.google.com/drive/folders/1-WP-RstPBJj2_gu1y4xZAqqhfX98cSty
2 - Medium | Avionics Engineering - Leading the way (Naslund) | Amy Burns / Tara Kraft |  | Leigh Parker ENG CONSOLIDATION (XA0) | Video Series | 2021-02-11 | 2021-02-22 | 2021-03-24 |  |  |  | Complete | John S.
2 - Medium | CMS Panorama Video | Kaitlin Johnston-Boyse |  | IO 265350 | Video | 2021-03-25 | 2021-04-06 | 2021-04-06 |  |  |  | Complete | John S. | Editing some video content add some graphics.
2 - Medium | Collins Aerospace Electronics CoP | John Kraemer |  | FY20 MS E&T Fellow - Kraemer (D) (000000263758) | Video | 2020-09-21 | 2020-09-21 |  | 10 |  |  | Complete | Kevin & John | Live to WebEx with PPT. Would like to be shot on green and have live switching to look like his other presentations. Will likely shoot in B108 Studio
2 - Medium | F-22 Program | Jessica Graham |  | C1RMG261 F22 Prelim Critcl Dsgn Rvw Conducted (000100140847 / 0508 / 0524) | Video | 2020-11-04 | 2020-10-16 | 2020-11-06 | 20 |  |  | Complete | Kevin O. | Introduction and tour of F22 labs for customer.
2 - Medium | FPO V1.0 Release Video | John Clemens |  | AP0171 CE TASAR Trial Development (000100140290 / 0060 | Script Review | 2020-11-20 | 2020-11-20 |  | 2 |  |  | Complete | John S. | See 11/19/2020 email for document. Kevin / John, Can either of you please review this potential script and make comments? I have already added my markup. Feel free to modify / add / replace from there. It should not take long to review. It would be great if you could have that completed by 11/20/2020 COB. But next week would be fine as well. If you have questions about it you can ask Michael McCarthy. You can also reply back to him with the markup when complete. Regards, John Clemens
2 - Medium | SPARTAN still photos | Nathan VanderHorn |  | GD1706 SPARTAN SYS-ENG Mgt CY21 (000100139001 / 0976 / 1132) | Still Photography |  |  | 2021-03-24 | 10 |  |  | Complete | Kevin & John
2 - Medium | Virtual Avionics Trainer (VAT) Marketing Video | Doug Forret |  | C6RD2020 RD VAP ROFP 100139324 0014 | Video | 2020-07-20 | 2020-08-21 |  | 16 |  |  | Complete | John S. | LIve on youtube
2 - Medium | Winter Weather Safety Video | Robert Archibald |  | KT6 | Video | 2020-09-07 | 2020-10-09 |  | 40-80 |  |  | Complete | John S. | We are thinking winter basics, walking techniques, proper shoes to wear, which doors to use under our current pandemic conditions, etc. John asked him to put together some rough bullet points/outline. Told him it'd take about the same amount of time as the temperature screening video that I made for Robert a few months back (depending on what we end up doing.)
2 - Medium | Z-Fab - Video Work Instructions (Shot 12/2/20) | Scot Marling/Mary Detweiler |  | GSBP2 ISD FY21 B&P (000100135817 / 0088 GSBP2 PTS Training Services FY21 B&P (000100135817 / 0090 | Video | 2020-11-10 | 2021-02-05 |  | 40-70 |  |  | Complete | John S. | John, I was given your name by Nate Oster. He said he has recently used your services for video footage. The project I am working on is a fairly complex process that we would like to have video footage to compliment our work instructions. The first segment of the process we want to capture is one that normally takes the better part of an 8 hour shift. Could you please let me know if you can help and possibly what the cost of an edited segment of that nature might be? Thank you, Scot Marling ---- Here's a cost estimate - Our department's hourly rate is $109/hr. Shooting the 8 hour process would prob take 10 hours to shoot (adding an hour for setup and an hour for teardown.)($1090) If the deliverable is similar to the z-fab video, the time to edit it down will probably 40-60 hours ($4360 to $6540) Let me know what you think. Old charge: GP1323 Production Work Instructions - Rescope (000100140221 / 0120 / 0248)
3 - Low | Airshow COVID Briefings | Dallas Miller |  | Airshow SWOPS Config (000000826641) | Video Series | ? | ? |  | ? |  |  | Complete | John S. | Sent to Dallas 11/13/20 - Came Back 3/5/21
3 - Low | EMI Video series | John Kraemer |  | FY20 MS E&T Fellow - Kraemer (D) (000000263758) | Video | 2019-03-15 | 2020-03-29 |  | 20 |  |  | Complete | Kevin O. | paused until John K is available in Fall
3 - Low | Jack Chat | Jackie Pelland |  | HR - Jack Chats (000000353685) | Video series | [6 empty] | Complete | Kevin O. | Another episode is shot and in production. We've worked ahead a bit, so not huge priority
3 - Low | Safran Video | Tiffany Murphy |  | Project Duke EOC - Billed to SAFRAN (000000775047) | Video Series | 2020-08-03 | 2020-08-04 |  | 10 |  |  | Complete | Kevin O. | This is wrapped unless we hear otherwise
2 - Medium | Airshow Safety Briefings (Arabic) | Dallas Miller/Molly Beatty |  | AIRSHOW (Y06) | Video Series | 2021-04-01 | 2021-06-11 |  | ? |  |  | Complete | John S. | Script is with vendor. Proofs approved, finals due June 11
2 - Medium | Airshow Safety Briefings (Russian) | Dallas Miller/Molly Beatty |  | AIRSHOW (Y06) | Video Series | 2021-04-01 | 2021-06-11 |  | ? |  |  | Complete | John S. | Script is with vendor. Proofs approved, finals due June 11
2 - Medium | Airshow Safety Briefings (Simplified Chinese) | Dallas Miller/Molly Beatty |  | AIRSHOW (Y06) | Video Series | 2021-04-01 | 2021-06-11 |  | ? |  |  | Complete | John S. | Script is with vendor. Proofs approved, finals due June 11
2 - Medium | Airshow Safety Briefings (Spanish) | Dallas Miller/Molly Beatty |  | AIRSHOW (Y06) | Video Series | 2021-04-01 | 2021-06-11 |  | ? |  |  | Complete | John S. | Script is with vendor. Proofs approved, finals due June 11
1 - High | Endura Beverage Maker Series 4610 | Eric Dufur/Dan Burton |  | EATIS17 340 Repair Training Video Record (000100128698 / 0920 / 0922) | Video series | 2020-01-08 | 2020-12-31 |  |  |  |  | Complete | Kevin & John | This set is a smaller set of videos that will use the 4510 set as well on the LMS.. being built on LMS then ready to release. Already have 523
1 - High | Endura Water Heater Series | Eric Dufur/Dan Burton |  | EATIS17 340 Repair Training Video Record (000100128698 / 0920 / 0922) | Video series | 2020-01-08 | 2020-12-31 |  |  |  |  | Complete | Kevin & John | This set is shot and being scripted.
1 - High | Modis 4615 Beverage Maker | Eric Dufur/Dan Burton |  | EATIS17 340 Repair Training Video Record (000100128698 / 0920 / 0922) | Video series | 2020-01-08 | 2020-12-31 |  |  |  |  | Complete | Kevin & John | This is is being reviewed with the customer and is ready to be built out in the LMS.
1 - High | Modis Water Heater | Eric Dufur/Dan Burton |  | EATIS17 340 Repair Training Video Record (000100128698 / 0920 / 0922) | Video series | 2020-01-08 | 2020-12-31 |  |  |  |  | Complete | Kevin & John | This is is being reviewed with the customer and is ready to be built out in the LMS.
1 - High | Work Transfer General Training | Scott Severson |  | NF0 | Traditional CBT | 2021-02-12 | [5 empty] | Complete | John S.
1 - High | Cable Simulation Video | John Kraemer |  | John's Fellow NWA | Video | 2021-06-16 | 2021-06-18 |  | 10 |  |  | Complete | Kevin O. | Session in Building 108 studio
2 - Medium | Airshow Safety Briefings (German) | Dallas Miller/Molly Beatty |  | AIRSHOW (Y06) | Video Series | 2021-06-01 | 2021-06-25 |  | ? |  |  | Complete | John S. | Script is with vendor.
2 - Medium | Airshow Safety Briefings (Portuguese) | Dallas Miller/Molly Beatty |  | AIRSHOW (Y06) | Video Series | 2021-06-01 | 2021-06-25 |  | ? |  |  | Complete | John S. | Script is with vendor.
1 - High | Smart Manufacturing Intro Video | Ed Anctil |  | KS8 | Video | 2020-11-24 | 2020-12-14 | 2021-07-09 | 16 |  |  | Complete | John S. | Word-smithed script sent to customer for approval of script - then we will send out for professional audio track.
1 - High | Smart Torque Tool (STT) Marketing Video | Scott Wandler / Andrew Re / Ed Anctil |  | KS8 | Video | 2021-05-06 | 2021-06-16 | 2021-07-06 |  |  |  | Complete | Kevin & John | Approver Chuck Stroo - the guy who will be giving the presentation about the torque tool.
1 - High | Avionics Engineering - Avionics leading the way (IMS) | Tara Kraft, Shannon Standing, Stephanie Vitrano |  | Leigh Parker ENG CONSOLIDATION (XA0) | Video series | 2021-03-01 |  | 2021-07-22 |  |  |  | Complete | John S. | Monthly quick hit. Managed in MS Teams instead of google.
1 - High | CMS: Orion Program Testimonial | Kaitlin Johnston-Boyse |  | IO 265350 | Video series | 2021-07-22 | 2021-08-31 |  |  |  |  | Complete | John S. | Editing some video content add some graphics. Usually a recorded zoom. Want's one a month.
1 - High | CMS: Videos - HTI | Kaitlin Johnston-Boyse |  | IO 265350 | Video series | 2021-06-01 | 2021-08-31 |  |  |  |  | Complete | John S. | Editing some video content add some graphics. Usually a recorded zoom. Want's one a month.
3 - Low | SPARC Airport Shoot | Sasha Oster |  | TBD | Video | 2021-03-08 |  |  | 40-60? |  |  | Waiting for more info | Kevin & John | Mid March (March 15) timeframe -- multicamera shoot
1 - High | Microelectronics Lab 33B: Lab Tour | Nate Oster |  | 100143721 0130 | Video | 2021-10-19 | 2021-11-03 |  |  |  |  | Complete | Kevin & John | Nate needs it to show on the 4th I think. Kevin working the edit. John shot footage.
2 - Medium | Student/Intern Videos | Jaime Zeets |  | FY21 MS E&T Student Prg (D) (000000265349) | Video | 2021-04-29 | [5 empty] | Complete | John S. | Record a few student events, make a thank you to the interns/CoOps at the end of the year. Make a short Promo video for the SEPP program - highlight some of the projects. Interns and CoOps leave the last week in July.
2 - Medium | MSTA-2000 Photo Shoot | Don McDill - PoC Jordan Roe - Charge Number Guy Paul Voelkel - Stakeholder - Lab Tom Applebee - Stakeholder - Lab |  | C1XMG2120-1N TCTS II Digital ATE (987-91 (000100144115 / 0002 / 0164) | Still Photography | 2022-01-05 | 2022-01-13 |  |  |  |  | Complete | John S. | Shooting a rig in 106 - Lab 23 - c/o Don McDill
1 - High | EHS the Basics Video | Robert Archibald / Adam Merritt |  | KT6 | Video | 2021-05-14 | [5 empty] | Complete | John S. | Basically, Remove Tom Gentner, remove UFO scene, Rebrand to Collins aerospace. If we need to re-cut parts, we can coordinate with Robert. Also, we can use Jack for any VO updates we need to bridge gaps between sections.
2 - Medium | Agile Albatross Airworthiness Flight Test prep | Nate VanderHorn |  | GQ011 CY22 Directional Comm IR&D? | Video | 2022-07-14 | [5 empty] | Complete | Kevin O.
2 - Medium | Engineering Week Leader Videos | Craig Bibeau |  | 266762 - FY22 MiS E&T CT3 Engineer Week (D) | Video | 2022-02-14 | 2022-02-18 |  | 16-32 |  |  | Complete | John S. | Found Footage - Leaders Record themselves -- The plan: Leaders from the Com/Nav/Guidance group will each record a 10-15 second cellphone video on why engineers week is important to them. There will probably be 15 to 20 people max making it about 4-5 minutes max
3 - Low | CMS 301 Edits | Jaime Zeets |  | FY22 MiS E&T CMS Training (D) (000000266814) | Video | [6 empty] | Complete | John S.
2 - Medium | WXR ILT Capture Videos | Kirk Thorson, John Clemmons, Stephanie Grant |  | TBD | Video series | TBD | TBD |  |  |  |  | Complete | TBD | Record ILT either in class or in studio. Create video series for likely LMS deployment. Recording in mid-July.
3 - Low | CL604 Fusion Video | Alick Zulu |  | BP853 EDS CL604 Validations (000100135861 / 0388 / 0486) | Video series | 2021-05-17 | 2021-06-30 |  | ? |  |  | Complete | Kevin & John | Multicam video shoot in CL604 Flightdeck to demostrate Fusion features
2 - Medium | Digital Engineering Video 2 - MiS - Process/Tools Improvement Communications | Jessica Muxen (called JJ) -- Milder Molly (JJ's Replacement -- Katrina Otis (via Kaitlin Johnston-Boyse) |  | GP1407 Knowledge Mgmt Q2 (000100145433 / 0188 / 0190) | Video series | 2022-04-10 | 2022-06-15 | June 15th | 80 |  |  | Complete | John S. | https://rtxusers.sharepoint.us/:w:/r/sites/DigitalEngineeringVideo-COL/_layouts/15/Doc.aspx?sourcedoc=%7B353AF3AB-9F5D-47B8-B324-E59B1EEEC1C3%7D&file=Digital%20Engineering%20Overview%20Links.docx&action=default&mobileredirect=true
1 - High | SPOTY Awards Video | Lauren Wymore |  | EQ8 | Video | 2022-05-01 | 2022-06-01 | 2022-06-29 | 80 |  |  | Complete | Kevin, John, & Mckenzie | Should know winners by May 27th, ceremony is June 8th. Mike Anderson will probably be the MC/Intro/Conc. Jack will be involved to help plan and write out the scripts. Last years ceremony - https://utc.mc.kontiki.com/global2/player?moid=5ea892f5-0c54-4c32-8908-f82eb2c21e26
3 - Low | 3500 Series Oven Testing | Dan Burton |  | GT1010 24262205 Galley Inserts Training (000100141047 / 1272 / 1274) | Video series | 2021-02-01 | 2022-05-01 |  | 40 |  |  | Complete | Kevin & John | New footage and narration script for final set. Customer would like to see on the LMS as soon as possible.
1 - High | Teklam Panel Process Videos (16 videos) | Warren Fitch, Kam Chan, Farhan Ahmed |  | EATIS17 366 Teklam Training Videos (000100128698 / 2272 / 2274) | Video series | Jan, 2022 | ongoing | 2022-07-01 | 60 |  |  | Complete | Kevin O. | Customer provided footage to edit in C.R.
2 - Medium | Training Assets Video | Dawn Barton |  | 266812 - Center of Learning | Video | Late May | 2022-06-10 |  | 20 |  |  | Complete | Kevin O. | Video studio shoot -- shot on may 13th
2 - Medium | SPARTACUS OPL Airport Shoot | Nate VanderHorn/Zach Haralson |  | GD1846 SPARTACUS Demo 1 Execution (000100142409 / 0456 / 0506) | Video | 2022-05-11 | ? |  | 20 |  |  | Complete | Kevin O. | OPL video shoot May 12
2 - Medium | Kestral Demo Video (short version) | Doug Webb |  | NWA: GP1327 100140366 0186 0190 | Video | 2022-06-01 | 2022-08-01 | 2022-07-15 | 150 |  |  | Complete | Kevin & John | Still planning how to approach. Provided Creative Brief template to Doug. Will have planning meeting upcoming to discuss.
2 - Medium | Internship Thank You Video | Jaime Zeets / Tara Kraft / Noah Hoadley |  | Avionics Eng Student Employee Programs (000000262627) | Video | 2022-07-05 | 2022-07-29 |  | 35-40 |  |  | Complete | Mckenzie
2 - Medium | Airshow Briefing Updates | Lauren Trosky |  | AIRSHOW (Y06) | Video | 2022-08-03 | 2022-08-04 |  | 4 |  |  | Complete | John S.
3 - Low | VSL University: Ron Major Video | Kathleen Armstrong |  | C62 | Video series | 2022-08-05 | 2022-08-10 |  | 30 |  |  | Complete | Kevin O. | Ongoing shooting of presentations in studio for VSL Kontiki channel.
2 - Medium | Griffin-2 Installation Filming | Christi Johnson |  | CSMU9177 JSF G2 Dome 1 Film Labor (000100144017 / 0292 / 0294) | Video | 2022-06-08 |  |  | 30 |  |  | Complete | Kevin & John | Vendor (Talking Heads - Orlando) to shoot the 3 weeks of footage and 3 camera 2 month timelapse. We edit the captured footage.
2 - Medium | Electrical Safe Work Practices ILT - Recording | Adam Merritt / Jeff Hynek |  | KT6? | Video | 2022-08-16 | 2022-08-18 | 2022-08-18 | 16? |  |  | Complete | John S.
2 - Medium | Kestral Demo Video | Doug Webb |  | NWA: GP1327 100140366 0186 0190 | Video | 2022-06-01 | 2022-08-01 |  | 150 |  |  | Complete | Kevin & John | Created short version for DARPA, adding lab footage to create final version.
2 - Medium | SPARTACUS Video Reel | Zach Haralson |  | GD1846 Spartacus Sys Engr Mgmt FY22 (000100142409 / 0300 / 0532) | Video | 2022-07-19 | 2022-07-20 |  | 20 |  |  | Complete | Kevin O. | OPL video shoot May 12
3 - Low | P-90 VR Demo Videos (2 videos) |  |  |  | Video Support | 2022-09-20 | 2022-09-23 |  | 30 |  | 0 | Complete | Kevin O. | Video loop of VR assets for customer demo.
3 - Low | DE&I - Quick Tik Tok style recording | Craig Bibeau / Amy Dupoise / Katie Allen |  | EA6 | Video | 2022-09-21 | 2022-09-26 |  | 15.5 | 15.5 | 0 | Complete | John S.
3 - Low | Avionics Engineering Employee Event Photography | Tara Kraft |  | 255815 Avionics Eng Employee Morale - Console | Still Photography | 2022-09-29 | 2022-09-30 |  | 8 |  | 0 | Not Started | John S. | Evening event at Bloomsbury Farm - they just want some record of it.
3 - Low | VAT (Vitrual Avionics Trainer) Glamor Photos | John Clemens |  | TBD | Still Photography | 2022-09-08 | 2022-09-09 |  | 4 |  | 0 | Waiting for more info | John S. | Somthing like this....https://rtxusers.sharepoint.us/:i:/r/sites/FileShare-COL/Shared%20Documents/General/MicrosoftTeams-image%20(5).png?csf=1&web=1&e=AvapPl
2 - Medium | IEEE Symposium Video | John Kraemer |  | Cat-U Curriculum Leadership (000000262229) | Video | 2022-10-05 | 2022-10-10 |  | 10 |  | 0 | Complete | Kevin O.
2 - Medium | All Hands Support at the Airport | Teresa Behnke / Val Humphrey |  | A69 | Video Support | 2022-10-11 | 2022-10-20 |  | 40 |  |  | DEAD | Kevin & John
3 - Low | Smart MFG: Automatic Optical Inspection Intro Re-shoot | Josh Rubin |  | AVI TOOL/DIG/ADV MFG (KS8) | Video | 2022-09-29 | 2022-10-07 |  | 10 |  | 0 | Complete | Kevin & John | Changing talent on the intro. Shoot new intro in studio.
3 - Low | P-90 VR Demo Videos |  |  | GK654 IS Virtual Reality suite for CEC (000100145951 / 0056 / 0180) | Video Support | 2022-09-20 | 2022-09-23 |  | 30 |  | 0 | Complete | Kevin O. | Video loop of VR assets for customer demo.
2 - Medium | Kestral Demo Video updates | Doug Webb |  | NWA: GP1327 100140366 0186 0190 | Video | 2022-06-01 | 2022-08-01 |  | 40 |  |  | Complete | Kevin & John | Created short version for DARPA, adding lab footage to create final version.
3 - Low | BMW - Video Upload to Kontiki | Matt Marks c/o Dawn Barton |  | FY22 MiS E&T CT3 BMW Feature Dev (D) (000000266797) | Video | 2022-10-31 | 2022-10-31 | 2022-10-31 | 1.5 | 1.5 | 1.5 | Complete | John S.
2 - Medium | Digital Engineering Podcast Ep 1 | Molly Milder (Katrina Otis via Kaitlin Johnston-Boyse) |  | GP1407 Workplace Culture Q4 (000100145433 / 0754 / 0760) | Podcast | 2022-10-26 | 2022-11-15 |  | 3 |  |  | Complete | Kevin & John | Prototype for new Podcast series recording on Oct 26.
2 - Medium | Digital Engineering Podcast Ep 2 | Molly Milder (Katrina Otis via Kaitlin Johnston-Boyse) |  | GP1407 Workplace Culture Q4 (000100145433 / 0754 / 0760) | Podcast | 2022-10-26 | 2022-11-15 |  | 3 |  |  | Complete | Kevin & John | Prototype for new Podcast series recording on Oct 26.
2 - Medium | Digital Engineering Podcast Ep 3 | Molly Milder (Katrina Otis via Kaitlin Johnston-Boyse) |  | GP1407 Workplace Culture Q4 (000100145433 / 0754 / 0760) | Podcast | 2022-10-26 | 2022-11-15 |  | 3 |  |  | Complete | Kevin & John | Prototype for new Podcast series recording on Oct 26.
2 - Medium | Griffin-2 Installation Training Editing (4 videos) | Christi Johnson |  | CSMU9172 CS FJ Install Trng Mtl Create (000100143360 / 0062 / 0064) | Video series | 2022-08-15 | 2022-09-30 |  | 48 |  | 0 | Complete | Kevin & John | Scripting and edting of training video. To be hosted on Kontiki. Waiting on feedback and more funding
2 - Medium | A220 Aural Alert Recording | Nick Helsper |  | BD857 ROAAS Sys Dev A220 (000100144575 / 0624 / 0698) | Audio | 2022-11-16 | 2022-12-01 |  | 5 |  |  | Complete | Kevin O. | Recording Craig and Tony Venuto for A220 A/C
1 - High | P90-VR Video Updates
1 - High | PRC-162 Manpack Radio Video Tutorials | Justin Bell, Preston Johnson, Barry Cheesman, Carles Toplikar |  | TAS PRC-162 TrainingVideos/OtherResoures (000100145944 / 1570 / 1580) | Video series | 2022-11-28 | 2022-12-23 |  | 40 |  |  | Complete | Kevin O. | Working on a bid for funding to produce 2 prototypes by end of year for the customer's portal page.
1 - High | Endura 3000 Oven Program (25 videos) | Dan Burton |  | GT1010 24262205 Galley Inserts Training (000100141047 / 1272 / 1274) | Video series | 2022-07-19 | 2022-12-23 |  | 250 | 240 | 0 | Complete | Kevin O. | Series of new videos for the LMS training. Nearly ready for LMS
2 - Medium | Digital Engineering Podcast Ep 4 | Molly Milder (Katrina Otis via Kaitlin Johnston-Boyse) |  | GP1407 Workplace Culture Q4 (000100145433 / 0754 / 0760) | Podcast | 2022-12-13 | 2022-12-15 |  | 3 |  |  | Complete | Kevin & John | Prototype for new Podcast series recording on Oct 26.
2 - Medium | Digital Engineering Podcast Ep 5 | Molly Milder (Katrina Otis via Kaitlin Johnston-Boyse) |  | GP1407 Workplace Culture Q4 (000100145433 / 0754 / 0760) | Podcast | 2023-01-06 | 2023-01-10 |  | 3 |  |  | Complete | Kevin & John | Prototype for new Podcast series recording on Oct 26.
1 - High | Proposal Narrative Training CBT Video and Narration | Heather Neiger |  | FY22 MiS BMW Pricing Training Video (000000267982) | Video Support | 2022-11-30 | 2022-12-23 |  | 10 |  |  | Complete | Kevin & John | Traditional CBT with some video and narration components. Kickoff 12/2
2 - Medium | Digital Engineering Video 3 - MiS - Process/Tools Improvement Communications | Molly Milder (Katrina Otis via Kaitlin Johnston-Boyse) |  | GP1407 Workplace Culture Q4 (000100145433 / 0754 / 0760) | Video series | 2022-09-08 | 2022-09-30 |  | 80 |  | 0 | Complete | John S. | https://rtxusers.sharepoint.us/:w:/r/sites/DigitalEngineeringVideo-COL/_layouts/15/Doc.aspx?sourcedoc=%7B353AF3AB-9F5D-47B8-B324-E59B1EEEC1C3%7D&file=Digital%20Engineering%20Overview%20Links.docx&action=default&mobileredirect=true
3 - Low | KC-46 Training - Intro to CSE | Rebecca Smith / Chris Carle |  | GB421 RVS2 CSE AVITA Training LOE 2023 (000100147951 / 0940 / 1028) | Video | 2023-02-10 | 2023-02-11 | 2023-02-11 | 4 | 3 |  | Complete | John S. | Zoom Recording. Final Video in link in the useful links section. | https://rtxusers.sharepoint.us/sites/KC46RVS2/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=6NsCnc&OR=Teams%2DHL&CT=1676051312029&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiIyOC8yMzAxMDEwMDkxMyIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&cid=f8ce3d2f%2D6fc2%2D4902%2D8a03%2D336afc108562&FolderCTID=0x012000FE326CACFDA6674D8AA99FB20F60F678&id=%2Fsites%2FKC46RVS2%2FShared%20Documents%2FTraining%20and%20Onboarding%2FLab%20Tools
1 - High | Customer Portal Virtual Tour Video | Logan Shortt/ Van Nong |  | 100144418 / 1150 GT010 JMBPTLS15 Cust Portal Video Spt | Video | 2022-08-25 | 2023-02-22 |  | 61.5 | 61 | 0 | 05-Complete | Kevin O. | Probably motion graphics of screen captures of Customer Portal. Created 2 previous versions. Customer asked for more changes, sent revised script Nov28. Need IDWA renewed with additional money.
2 - Medium | Imminent Threat System Video or CBT | Rob Archibald |  | Split between KT6 and EQ7 | Video | 2023-02-01 | [5 empty] | 05-Complete | Kevin O. | Basically, they want the old video re-branded to Collins instead of Rockwell Collins and they want to re-cut the audio with a different narrator.
2 - Medium | Digital Engineering Video 4 - MiS - Roadshow Video | Molly Milder (Katrina Otis via Kaitlin Johnston-Boyse) |  | GP1407 Workplace Culture Q4 (000100145433 / 0754 / 0760) | Video series | 2022-12-13 | 2/30/2023 |  | 80 |  | 0 | 05-Complete | John S.
2 - Medium | Women's History Month Celebration | Tiffany Dague |  | TBD | Video Support | 2023-03-30 |  |  | 6 |  |  | 05-Complete | Kevin & John | 106 Auditorium shoot/stream support
3 - Low | Boeing Aural Alerts Recording | Emmanuel Derouillat |  | AP0712 B777X PM Material 100117344 0526 | Audio Alerts | -- |  |  | 2 |  |  | 05-Complete | Kevin O.
2 - Medium | Introduction of Pillars & Pillar Single Source of Truth | Katrina Otis |  | GMS178-Workforce and Culture (000100144925 / 0030 / 0068) | Podcast | 2023-02-16 | 2023-02-22 |  | 2 |  |  | 05-Complete | Kevin O.
2 - Medium | Gitlab Podcast Recording | Katrina Otis |  | GMS178-Workforce and Culture (000100144925 / 0030 / 0068) | Podcast | 2023-02-02 | 2023-02-03 |  | 4 |  |  | 05-Complete | Kevin O.
2 - Medium | Collins Creative Cloud Library 2023 | Jeff Andrus |  | G13 | Video | 2022-12-24 |  |  | 8 | 1 | 7 | In-Review | John S. | Update Creative Cloud Library for branding.
2 - Medium | Embedded Computing Conference Recordings 2022 | Tara Kraft |  | Avionics Engineering Fellow - Corbett (000000261742) | Video series | 2022-12-01 | 2023-01-01 |  | 23 | 0 | 23 | In-Review | John S. | Customer Tara Kraft. They have 23 zoom presentations that need to be trimmed and standardized (front slide and collins logo at the end.) -- Need to contain throughout the words "No Tech Data" and must contain "export classification id #" -- Due December/January
2 - Medium | SMART MFG: Adaptive Material Removal (AMR- Burnsville) | Ed Anctil / Josh Rubin |  | KS8? | Video |  |  |  | 80 |  |  | 05-Complete | Kevin O. | Robotic grinder that removes carcinogens from parts and grinds and polishes components into shapes - like pitot tubes. Protects people who did it manually.
2 - Medium | SMART MFG: Auto braze (Burnsville) | Ed Anctil / Josh Rubin |  | KS8? | Video |  |  |  | 80 |  |  | 05-Complete | John S. | Robotic brazing for pitot tubes. eliminates mess and variablity from doing it by hand.
2 - Medium | SMART MFG: Automated Optical Inspection (AOI -Burnsville) | Ed Anctil / Josh Rubin |  | KS8? | Video |  |  |  | 80 |  |  | 05-Complete | John S. | Robotic scanner and camera that makes a super duper high resolution 3d model for inspection purposes. It scans depth with a lazer and takes photos with an optical camera and merges it all together.
2 - Medium | Icon Work for the ICS group | Dinesh Patil |  | TPP101 Software Development (100145073 / 0058 / XXXX) | Graphics Support | 2023-01-30 | [5 empty] | 04-In-Review | John S. | Updating some graphics for the ICS group.
3 - Low | Avionics Leader Summit | Tara Kraft |  | XA0 | Still Photography | 2023-04-25 |  |  | 2025-08-10 |  |  | 00-Not Started | John S. | Shooting an event at the Kirkwood hotel.
3 - Low | KC-46 Training - CSE VRCU Test Stand | Rebecca Smith / Chris Carle |  | GB421 RVS2 CSE AVITA Training LOE 2023 (000100147951 / 0940 / 1028) | Video | 2023-02-10 | 2023-02-11 | 2023-02-11 | 4 | 3 |  | Complete | John S. | Zoom Recording. Final Video in link in the useful links section. | https://rtxusers.sharepoint.us/sites/KC46RVS2/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=6NsCnc&OR=Teams%2DHL&CT=1676051312029&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiIyOC8yMzAxMDEwMDkxMyIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&cid=f8ce3d2f%2D6fc2%2D4902%2D8a03%2D336afc108562&FolderCTID=0x012000FE326CACFDA6674D8AA99FB20F60F678&id=%2Fsites%2FKC46RVS2%2FShared%20Documents%2FTraining%20and%20Onboarding%2FLab%20Tools
3 - Low | KC-46 Training - VPU Test Stand | Rebecca Smith / Chris Carle |  | GB421 RVS2 CSE AVITA Training LOE 2023 (000100147951 / 0940 / 1028) | Video | 2023-02-10 | 2023-02-11 | 2023-02-11 | 4 | 3 |  | Complete | John S. | Zoom Recording. Final Video in link in the useful links section. | https://rtxusers.sharepoint.us/sites/KC46RVS2/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=6NsCnc&OR=Teams%2DHL&CT=1676051312029&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiIyOC8yMzAxMDEwMDkxMyIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&cid=f8ce3d2f%2D6fc2%2D4902%2D8a03%2D336afc108562&FolderCTID=0x012000FE326CACFDA6674D8AA99FB20F60F678&id=%2Fsites%2FKC46RVS2%2FShared%20Documents%2FTraining%20and%20Onboarding%2FLab%20Tools
3 - Low | KC-46 Training - CSE Boot Camp | Rebecca Smith / Chris Carle |  | GB421 RVS2 CSE AVITA Training LOE 2023 (000100147951 / 0940 / 1028) | Video | 2023-02-10 | 2023-02-11 | 2023-02-11 | 4 | 3 |  | Complete | John S. | Zoom Recording. Final Video in link in the useful links section. | https://rtxusers.sharepoint.us/sites/KC46RVS2/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=6NsCnc&OR=Teams%2DHL&CT=1676051312029&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiIyOC8yMzAxMDEwMDkxMyIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D&cid=f8ce3d2f%2D6fc2%2D4902%2D8a03%2D336afc108562&FolderCTID=0x012000FE326CACFDA6674D8AA99FB20F60F678&id=%2Fsites%2FKC46RVS2%2FShared%20Documents%2FTraining%20and%20Onboarding%2FLab%20Tools
3 - Low | VAT - C295 - Photos | Paul Langholz / Joan Davis |  | C6L3HAR L3 C295 eDTD Graphics 100149111 0002 | Still Photography | 2023-05-08 | [5 empty] | 00-Planning | John S. | I do have a Q2 need. For the C295 project, once Joan finishes assembling the training device, I need some pictures taken of the unit for a document. Is there someone on your team in Cedar Rapids who could do that? I’m thinking Joan will be done by May 8th. Let me know if someone could snap a few pictures that week for us. NWA is C6L3HAR L3 C295 eDTD Graphics 100149111 0002 Thanks. Paul
2 - Medium | Radio Shoot for slick sheets | Josh Pollak / Eileen Horan |  | 100149545/0026/0028 | Still Photography | 2023-05-08
2 - Medium | SPOTY | Becca Ries |  | TBD | Video | May | 2023-06-06 |  | 146 |  |  | 03-In process
2 - Medium | Advanced Manufacturing Photos | Chase Bennett / Scott Wandler |  | KS8 | Still Photography | 2023-04-12 | [5 empty] | 00-Planning | Kevin & John | Shoot some photos of the Smart Manufacturing Capablities
3 - Low | EDATS Catalog Photos | Tony Stephens / Matt Juszczyk |  | KB2 | Still Photography | [6 empty] | 05-Complete | John S. | They're putting together a DATS catalog of their product line and want photos.
4 - Low | Seven Segment Font | Mario Andreani |  | C6TPS23 CS VAP Training Devices (000100149485 / 0026 / 0072) | Font Work | 2023-06-30 | 2023-06-30 | 2023-06-30 |  |  |  | 05-Complete | John S.
2 - Medium | RFID Video | Chase Bennett |  | KS8 | Video | [6 empty] | 04-In-Review | Kevin & John | May or June video in Melbourne .
2 - Medium | ABC Success Story - Mike Anderson | Roberta Cortez |  | 2023 Avionics Eng PEPP Facilitation (000000268934) | Video | 2023-09-18 | 2023-09-29 | 2023-09-29 |  |  |  | 04-In-Review | Kevin & John
2 - Medium | VR Trainer Video | Doug Forret |  | Program Oversite (000100131489 / 0510 / 0644) | Video | 2023-09-20 | [5 empty] | 03-In process | John S.
2 - Medium | Phil Jasper - Strategic Imperatives | Kevin Thomas |  | GS Exec (E64) | Video | 2023-09-25 | 2023-09-28 | 2023-09-29 |  |  |  | 04-In-Review | Kevin & John
1 - High | Common Technology Tools Team (CT3) on a promotional video | Erin Paul |  | Split Between: FY23 MiS E&T CT3 BMW/Propricr Sustain(D) (000000267993) FY23 MiS E&T CT3 ISAT Sustain (D) (000000267996) FY23 MiS E&T CT3 PARS Sustain (D) (000000267994) FY23 MiS E&T CT3 Staff Ctr WebSustain(D) (000000267995) | Video | [6 empty] | 04-In-Review | John S. | They want something that is a high-level overview of their dept, what tools and support they offer, etc. I originally thought of using the Vyond tool to create something, but they’d like a more professional look (which makes sense). I don’t see this being a very long video – maybe 2-4 minutes.
2 - Medium | Pillar Formal Expression | Katrina Otis |  | GMS178-Workforce and Culture (000100144925 / 0030 / 0068) | Podcast | 2023-02-15 | 2023-02-20 |  | 2 |  |  | 05-Complete | Kevin O.
2 - Medium | Pillar Visual Intuitiveness | Katrina Otis |  | GMS178-Workforce and Culture (000100144925 / 0030 / 0068) | Podcast | 2023-02-15 | 2023-02-20 |  | 2 |  |  | 05-Complete | Kevin O.
2 - Medium | Pillar Automation | Katrina Otis |  | GMS178-Workforce and Culture (000100144925 / 0030 / 0068) | Podcast | 2023-02-15 | 2023-02-20 |  | 2 |  |  | 05-Complete | Kevin O.
2 - Medium | IDE Process and Data Definitions Podcast | Katrina Otis |  | GMS178-Workforce and Culture (000100144925 / 0030 / 0068) | Podcast | 2023-05-19 | 2023-05-23 |  | 4 |  |  | 05-Complete | Kevin O.
2 - Medium | C130 Audio Alerts | Logan Fleming |  | GB1300 C130AMP Grnd Flight TestSupt 2023 (000100147062 / 0548 | Audio Alerts | [6 empty] | 05-Complete | Kevin O.
1 - High | Landing Safety Video -Vets Day Video | Brandy Dunn |  | GT1010 26708496 Landing Sys Sfty Video (000100149761 / 0650 / 0652) | Video | 2023-10-30 | 2023-11-10 | 2023-01-01 | 20 | 8 |  | 05-Complete | Kevin O. | Stich together set of customer supplied videos
3 - Low | SPARTACUS Outtakes | Nate Vanderhorn |  | GD1846 SPARTACUS CloseOut (000100142409 / 0784 / 0800) | Video series | 2023-08-31 | 2023-09-15 | 2023-09-08 | 40 |  |  | 05-Complete | Kevin O.
1 - High | SPARTACUS | Nate Vanderhorn |  | GD1846 SPARTACUS CloseOut (000100142409 / 0784 / 0800) | Video series | 2023-08-31 | 2023-09-15 | 2023-09-08 | 40 |  |  | 05-Complete | Kevin O.
2 - Medium | Virtual Learning Rig | Richard Hansen |  | RCCAC Test Equipment (643280) | R&D | 2022-12-15 |  |  | 4 | 0.5 | 3.5 | 05-Complete | John S. | Training video about how to assemble. I got the sense that Rich, didn't really want feedback on how the rig was constructed. 7-VIDEOS
3 - Low | Stage Video Training-Selecting Content | Chris Miller-Franki Moehnke |  | Airshow SWOPS Marketing (000000826644) | Video series | -- | [5 empty] | 05-Complete | Kevin O. | Footage shot on 4/18/23
3 - Low | Stage Video Training-PC Sync | Chris Miller-Franki Moehnke |  | Airshow SWOPS Marketing (000000826644) | Video series | -- | [5 empty] | 05-Complete | Kevin O. | Footage shot on 4/18/23
2 - Medium | Mike Anderson Video Series "Open Mike" Ep 1 | JIll Wojciechowski |  | TBD | Video series | [6 empty] | 05-Complete | Kevin & John | Working on prototype for series shot by Mike and edited by us. Some interviews shot in studio.
2 - Medium | Mike Anderson Video Series "Open Mike" Ep 2 | JIll Wojciechowski |  | TBD | Video series | [6 empty] | 05-Complete | Kevin & John | Working on prototype for series shot by Mike and edited by us. Some interviews shot in studio.
2 - Medium | Mike Anderson Video Series "Open Mike" Ep 3 | JIll Wojciechowski |  | TBD | Video series | [6 empty] | 05-Complete | Kevin & John | Working on prototype for series shot by Mike and edited by us. Some interviews shot in studio.
2 - Medium | Mike Anderson Video Series "Open Mike" Ep 4 | JIll Wojciechowski |  | TBD | Video series | [6 empty] | 05-Complete | Kevin & John | Working on prototype for series shot by Mike and edited by us. Some interviews shot in studio.
2 - Medium | Mike Anderson Video Series "Open Mike" Ep 5 | JIll Wojciechowski |  | TBD | Video series | [6 empty] | 05-Complete | Kevin & John | Working on prototype for series shot by Mike and edited by us. Some interviews shot in studio.
2 - Medium | Mike Anderson Video Series "Open Mike" Ep 6 | JIll Wojciechowski |  | TBD | Video series | [6 empty] | 05-Complete | Kevin & John | Working on prototype for series shot by Mike and edited by us. Some interviews shot in studio.
3 - Low | A220 Aural Alert Recording update | Nick Stout |  | TBD | Video | [6 empty] | 05-Complete
2 - Medium | Airshow Dassult Safety Video Updates | Tyler Canfield |  | Airshow SWOPS Marketing (000000826644) | Video series | 2023-10-01 | 2023-12-01 |  | 40 |  |  | 05-Complete | Kevin & John | Make updates to Dassult safety videos as requested by customer
1 - High | Landing Safety Video | Brandy Dunn |  | GT1010 26708496 Landing Sys Sfty Video (000100149761 / 0650 / 0652) | Video | 2023-09-27 | 2023-10-01 | 2023-09-29 |  |  |  | 05-Complete | Kevin O. | Stich together set of customer supplied videos
2 - Medium | Mike Anderson Video Series "Open Mike" Ep 7 | Kevin Thomas |  | E40 | Video series | [6 empty] | 05-Complete | Kevin & John | Working on prototype for series shot by Mike and edited by us. Some interviews shot in studio.
1 - High | Intertrade End of Year Video | Chase Enright |  | RCS INTRTRDE MKTNG (P06) | Video | 2023-12-01 | 2023-12-01 |  |  |  |  | 05-Complete | Kevin & John
2 - Medium | Rig Photos and Photogrammetry - John Clemens Rig | John Clemens |  | Program Oversite (000100131489 / 0510 / 0644) | Still Photography | 2023-09-26 | [5 empty] | 05-Complete | John S.
1 - High | Tailwind Video shoot - Melbourne, FL | Phil Clay, Chris Miller |  | PTS-BRA Systems Video Development100135848 3750 | Video | 2023-10-17 | [5 empty] | 05-Complete | Kevin & John
3 - Low | Winter Safety Program - Cheshire | Nancie Munselle / Liz Welsh |  | TBD | Video | 2023-10-24 |  |  | 40 | 0 | 0 | 05-Complete |  | They want the training updated to feature the Cheshire site of Collins. They want salt boxes added to the training.They want the logo at the beginning and end updated to current branding.
2 - Medium | Mike Anderson Video Series "Open Mike" Ep 8 | Leah Durain |  | E40 | Video series | [6 empty] | 05-Complete | Kevin & John | Working on prototype for series shot by Mike and edited by us. Some interviews shot in studio.
🔥ON FIRE🔥 | Simplimatics Video | Dan Christensen |  | Manpack - Sub-Assembly Automation (000000268183) | Video | [6 empty] | 05-Complete | Kevin & John
2 - Medium | PTS Town Hall | Michelle Mcullough |  | N05 | Video Support |  | 2023-12-14 |  |  |  |  | 05-Complete | Kevin & John | Shoot in ISU room
1 - High | Landing Safety Year End Video | Brandy Dunn |  | GT1010 26708496 Landing Sys Sfty Video (000100149761 / 0650 / 0652) | Video | 2023-12-04 | 2023-12-15 |  |  |  |  | 05-Complete | Kevin O. | Stich together set of customer supplied videos
3 - Low | Lab 66 photos/video | Don McDill / Laura Killberg / Matt Galyean |  | MA&H - Type 37 Collateral Special Proj (000000265863) | Video | 2023-12-08 | 2024-01-13 |  |  |  |  | 05-Complete | John S.
2 - Medium | LADS: How it works - Video 1 | Aaron Wesser |  | 27196591 - LADS Marketing - Studio 153 (000000270331) | Video | 2023-10-03 | 2023-12-23 |  | 8 | 0 | 0 | 03-In process | John S. | Old-GT1010 26781089 LADS Marketing Supt (000100149761 / 0752 / 0754)
1 - High | Innovation Day Q2 | Pavan Chinta |  | XG5 | Video |  |  |  | 16 |  |  | 05-Complete | Kevin O. | Two videos for FMS innovation day
1 - High | Innovation Day Q1 | Pavan Chinta |  | XG5 | Video |  |  |  | 16 |  |  | 05-Complete | Kevin O. | Two videos for FMS innovation day
1 - High | F-35 Head Scan Tech Pad Visor Milling Process Video | Laura Kilburg / Dustin Vagedes / Matt Soukup / Larry Covington |  | 000000260760MarCom - Services Short Marketing Videos (000000260760) | Video series | March | March |  |  |  |  | 05-Complete | Kevin & John | We are looking to create some video in 153 using our head scan tech and our pad/visor milling process. The demo room is in 153. We want three short 30-60 videos of: The head scanning process, the mill of a pad and the mill of a visor. Can we get a price quote and what you need to perform the video? We will have to record in the 153 demo room, so if we need a white backdrop or lighting, how does that work? Looking for asap - in the next 3-4 weeks.
2 - Medium | Hyperlynx DRC CATU Training Course (12 videos) | Matt Juszczyk |  | Cat-U Curriculum Leadership (000000262229) | Video series | 2022-12-05 | 2022-12-23 |  | 40 | 0 | 0 | 05-Complete | Kevin & John | Series of 6 videos teaching Hyperlync DRC. Shot in studio
2 - Medium | Mike Anderson Video Series "Open Mike" Ep 9 | Leah Durain |  | E40 | Video series | [6 empty] | 05-Complete | Kevin & John | Shoot Jan 2
1 - High | Engineer of the Year (28 short videos - 1 big one - stream via zoom) | Tara Kraft |  | Avionics Eng - Eng of the Year (000000261730) | Video Set | 2024-01-11 | 2024-02-16 |  | 160 |  |  | 05-Complete | Kevin & John | Show Streams 2/19 - Wired quoted 20K on the video creation - we have to stay under that (166hr)
2 - Medium | Intertrade Video | Chase Enright |  |  | Video | [6 empty] | 05-Complete | Kevin O.
3 - Low | Turkish ASOJ (Missionized M145) Aural Alerts | Brand Shaw |  | TBD | [7 empty] | 05-Complete | Kevin O.
1 - High | MiS Ops Safety Week | Kevin Thomas |  | E64 | Video | [6 empty] | 05-Complete |  | SHOOT JAN 3
1 - High | RCTS-4000 Equipment Photos | Don McDill |  |  | Still Photography |  |  |  | 24 | 0.5 | 0 | 05-Complete | Kevin & John | $3-5k - Video acquasition too.
3 - Low | VR Trainer video update | Doug Forret |  | Program Oversite (000100131489 / 0510 / 0644) | Video | 2024-01-11 | 2024-01-12 |  | 1 |  |  | 05-Complete | John S.
2 - Medium | Mike Anderson - Open Mike - EP-10 | Leah Durain/Erin Paul |  | E40 | Video series | [6 empty] | 05-Complete | Kevin & John
2 - Medium | Mike Anderson - Open Mike - EP-11 | Leah Durain/Erin Paul |  | E40 | Video series | [6 empty] | 05-Complete | Kevin & John
3 - Low | Coralville Townhall | George Mahoney |  | OPS CVL ADMIN (M89) | Video
2 - Medium | SPOTY | Becca Ries |  | E40/EQ8 | Video | May | 2024-06-06 |  | 146 |  |  | 03-In process | Kevin & John
2 - Medium | Venue Smart Monitor photo shoot | Johnse Bushlack |  | Marcom - BDUx (Cabin Display) Adv (000000268343) | Still Photography | 2024-01-25 | 2024-01-29 |  | 8 |  |  | 00-Planning | John S. | Creative Turntable Footage - with light wand (maybe Christmas lights in the background - Macro Photogrammetry Footage Product Shots/Still for brochure. Footage for Vendor to use. Video and stills. Maybe some shots in a lab.
1 - High | Mike Anderson - Open Mike - SPOTY | Leah Durain/Erin Paul |  | E40 | Video series | [6 empty] | 03-In process | Kevin & John
3 - Low | National Intern Day | Tara Kraft |  | IO 000000262627 | Video |  |  |  | 4 |  |  | 01-Ready | John S. | We basically just want a still or moving graphic to put on the large movie theater screen as they enter the theater. We'll take a group photo of the students in front of it.
3 - Low | FMS NEXT EXPO Graphics | Chris W Vincent |  | BD905 NG Ph1 Architecture (000100154989 / 0094) | Video | 2024-07-22 | 2024-08-08 |  |  |  |  | 05-Complete | John S.
2 - Medium | Digital Engineering Video K8 & Dewey Character Demo | Molly Milder (Katrina Otis via Kaitlin Johnston-Boyse) |  | GP1407 Knowledge Mgmt Q2 (000100145433 / 0188 / 0190) | Video | 2022-07-22 | 2022-08-05 |  | 40 |  |  | 05-Complete | John S.
2 - Medium | Mike Anderson - Open Mike - EP-12-ESP | Leah Durain/Erin Paul |  | E40 | Video series | [6 empty] | 05-Complete | Kevin & John
2 - Medium | ICS Video Training | Kirk Thorson |  | PTS-BRA Systems Video Development100135848 3750 | Video | [6 empty] | 05-Complete | Kevin O. | Shoot ICS rig in Little Rock first or second quarter Shoot moved to CR rig
2 - Medium | Intertrade Headshots | Chase Enright |  | RCS INTRTRDE MKTNG (P06) | Still Photography | [6 empty] | 05-Complete | John S.
2 - Medium | Smart MFG: CIMCO equipment analysis tool | Josh Rubin / Chase Bennett |  | AVI TOOL/DIG/ADV MFG (KS8) | Video | Q1 2023 | Q1 2023 | Q1 2023 | 80 |  | 0 | 05-Complete | Kevin & John | We’d be looking to promote this system when it’s fully implemented in Bellevue, STARTING UP Q1 24 -- Moved to Decorah.. Probably shooting in June
🔥ON FIRE🔥 | Air Rest Seating videos | Jimmy Swaim / Jason Willette |  | 27414213 - Prod Training Video - Air Res (000000270670) | Video | May | 2024-06-06 |  | 40 |  |  | 05-Complete | Kevin & John | 2 videos
🔥ON FIRE🔥 | Oxygen Mask PBE Videos | Ted Marsh |  | 27750780 - Sustaining-PBE_Lenexa (000000270785) (~30hrs) 27516352 - Sustaining-PBE (000000270940) (~75hrs) | Video | May | 2024-06-06 |  | 110 |  |  | 05-Complete | Kevin & John | 2 Videos
3 - Low | VR Trainer Marketing DVD | Doug Forret |  | TBD -- C6TRUY18 100131489 0510? | Video Support | 2024-08-16 | 2024-08-19 |  | 2 to 3 |  |  | 00-Not Started |  | Just needs some clips put on a DVD
3 - Low | Icon work for Airshow/ICS | Krishna Kachroo |  | TPP102 ICS Sustainment SW (000100149811 / 0052 / XXXX) | Graphics Support | 2024-08-15 | 2024-08-16 |  | 1 to 2 |  |  | 03-In process |  | They just need a quick SVG of an image.
3 - Low | B110 Wastewater Treatment Video | Chris Shakespear |  |  | Video | 2024-09-25 | [5 empty] | 05-Complete | Kevin O. | Michelle recorded video
2 - Medium | AFD-2130 Video Capture | Dustin Krueger |  | TAS C-17 Flight Deck Replacement (000100149751 / 1092 / | Video | 2024-09-11 |  |  | 16 |  |  | 05-Complete | John S. | Capturing a display at different temperatures.
1 - High | TINA Introductions | Mike Gonzalez |  | GZ6 | Video | 2024-11-08 | [5 empty] | 05-Complete | Kevin O.
1 - High | Landing Systems Employee Appreciation Week Video | Brandy K. Dunn |  | Charge Number Questions: Charge Number: 7677P18110 Charge Number Description: LS Administration Profit Center: CCOTHR00 | [7 empty] | 05-Complete | Kevin O. | Landing Systems is looking to create a video for our upcoming Employee Appreciation Week the first week of September. We’re envisioning the video starting off with some animated history of our business unit (30 secs max) followed by an appreciation message compiled of clips from our senior leaders (similar to the safety video we did in September 2023). Is this something your team would have availability to help with? We’re looking to release the video on September 9.
2 - Medium | Product Line Strategy Workshop (PLSW) | Matt Mulnik |  |  | Video | [6 empty] | 05-Complete
2 - Medium | Project Missouri - Timelapse | Nick Morris / Nate Boelkins |  | 100155447 0202 – W/C N05-PMO 100155447 0204 – W/C N05-PROJ 100155447 0206 – W/C N05-MEDI | Video | March-Sept |  |  | 56 |  |  | 05-Complete | Kevin & John | Timelapse of new customer area being constructed near the coffee shop in the C Avenue complex. 2 hours per week x 24 weeks = 48 8 hours of final processing 56 hours total Hourly rate = $122 per/h x 56 hours = $6832.
2 - Medium | Software Control Library | Brittney Hoffman |  |  | Video | 2024-08-22 | 2024-08-22 |  | 8 |  |  | 05-Complete | Kevin O. | Scott Fuemmeler
3 - Low | AirShow: generic video briefings replace craft with F50EX airplane (English only) | Lauren Trosky |  | Airshow SWOPS Config (000000826641) | Video | Fall |  |  | 40 |  |  | 05-Complete | John S. | Generic video briefings. There's a customer requesting their F50EX plane be inserted into those videos in place of the generic falcon model. They are also requesting slightly revised versions of the script. (Audio updates) Once the livery is done, Lauren will send us the 3D file.
3 - Low | FMS NEXT EXPO Graphics | Chris W Vincent |  | BD905 NG Ph1 Architecture (000100154989 / 0094) | Video | 2024-07-22 | 2024-08-08 |  |  |  |  | 01-Ready | John S. | Updates needed
1 - High | EHS: Distracted Walking Video | Adam Merritt / Rob Archibald |  | KT6 | Video | 2024-08-29 | 2024-09-13 |  | 40? |  |  | 04-In-Review | Kevin & John | Looking into 2024 EHS wants to create a video like the winter walking video that deals with distracted walking, aisle & pedestrians and maybe one other topic. I am guessing it would be around 5-7 minutes. I am working on a list of items we want to include but here is our initial. • Distracted Walking/Driving- Which would include PIV/Bicycles and Pargos • Stopping at stop signs (We added some projection stop signs in manufacturing in 108 which would be good, we want everyone to stop at them regardless if you are driving something or walking • Using a handrail going up and down the stairs.
1 - High | CAS Year End Video | Breanne Sykes |  | CA500 | Video | 2024-12-09 | 2024-12-18 |  |  |  |  | 00-Planning | John S. | Last Year's CAS Video: https://video.rtx.com/media/t/1_kuafugyv Example John Sent over: https://video.rtx.com/media/t/1_qq42ctx7 We're hoping to record individuals via Zoom on 12/6, capturing their quick line of: "I'm a CAS employee, of course I [insert info]." I lean on your expertise here (cards vs recording)... We could do a quick intro card that says "I'm a CAS employee, of course I..." then go to the first person, then each person after that says the full line, and then we end with a "thank you for a great 2024 (or something like that) card. Here are a couple of examples of the trend https://www.instagram.com/southerncompany/reel/C558iumJYLY/ https://www.instagram.com/reel/C3abIz7MRKu/
1 - High | Mission Systems EOY Video 2024 | Maria Paulsen |  |  | Video | 2024-12-04 | [5 empty] | 00-Not Started | Kevin & John
1 - High | Nate Boelkin's Photoshoot CCC | Leah Durain |  | X33 | Still Photography | 2024-11-26 | [5 empty] | 00-Planning | John S. | I’m reaching out to see if you or another member of the Studio 153 team would be able to grab a few photos for us in the collaboration center? Long story short, photos from a recent Chris Calio visit were not approved to use with an internal article on the space so we’re hoping to grab a few with Nate Boelkins instead. It’s looking like we can book Nate for 30 mins on either November 25 or 26. Is there a time in there that would work for you? We’re looking for a shot like the one attached but a bit brighter if possible. This one is angled so as not to show certain products. And then a few shots of Nate and a couple other folks outside the space. (Posed group photo style) I heard there is a graphic on the wall now which could be cool.
2 - Medium | End of Year Message Emily Buckman | Teresa Armstrong |  | 28599767 - Gratitude Video Project (000000272028) | Video | [6 empty] | 03-In process | Kevin & John
3 - Low | CMS Video | Dawn Barton |  | J54 | Video | [6 empty] | 05-Complete | Kevin O.
1 - High | VPGM Video | Jaena West |  | X33 | Video | 2024-12-04 | [5 empty] | 05-Complete | Kevin & John | Teleprompter in studio shoot
1 - High | Engineer of the Year Mission Systems | Jaime Zeets |  | FY25 MiS E&T Eng Program Mtrl (272409) (000000275845) | Video |  | 2025-02-14 |  |  |  |  | 05-Complete | John S.
1 - High | Engineer of the Year Avionics | Tara Kraft |  | Avionics Eng - Eng of the Year (261730) (000000275411) | Video |  | 2025-02-14 |  |  |  |  | 05-Complete | John S.
2 - Medium | Autonomous Mobile Robots (AMR) | Josh Rubin / Chase Bennett |  | 276268-Studio 153 (000000276442) | Video | 2023-08-05 | 2024-11-15 |  | 160 |  |  | 05-Complete |  | Kicked off August 23, shooting in September
1 - High | C4I&A | Erin Paul |  | Jason Betts number? | Video | [6 empty] | 05-Complete | Kevin & John | Jason Betts’ organization would like to produce two short videos. These videos will be 1-2 minutes of Jason talking about his C4I&A organization and Gretchen Mock discussing the BMC2&A department within C4I&A. Filming should take no more than an hour and I was thinking we could have them back-to-back. Are you able to help with this initiative? I would like to have the same set up that we had for Mike when we filmed the Engineering Project Health Dashboard video in the exec conference room area (prompter/one camera). We are looking at filming the first or second week in December. Please let me know if you can assist.
2 - Medium | Tech Docs All Hands Video |  |  | General Time Overhead | Video Support | [6 empty] | 05-Complete | Kevin & John
1 - High | Engineering Stockroom: Engineering Labs Virtual Open House | Jeff Calloway--Brian Stapley (out on Sept 3) - Bill C. Pearson. and Mike Buscher |  | E36 | Video series | [6 empty] | 05-Complete | Kevin & John
1 - High | Lab 42 : Engineering Labs Virtual Open House | Brian Stapley (out on Sept 3) - Bill C. Pearson. and Mike Buscher |  | E36 | Video series | 2021-03-23 | 2021-12-17 |  |  |  |  | 05-Complete | Kevin & John
1 - High | Mech Shop : Engineering Labs Virtual Open House | Jeff Calloway--Brian Stapley (out on Sept 3) - Bill C. Pearson. and Mike Buscher |  | E36 | Video series | 2021-03-23 | 2021-12-17 |  |  |  |  | 05-Complete | Kevin & John
1 - High | Power Electronics: Engineering Labs Virtual Open House | Jeff Calloway--Brian Stapley (out on Sept 3) - Bill C. Pearson. and Mike Buscher |  | E36 | Video series | [6 empty] | 05-Complete | Kevin & John
1 - High | Vergennes VT - Model Shop: Engineering Labs Virtual Open House | Jeff Calloway--Brian Stapley and Mike Buscher |  | E36 | Video series | [6 empty] | 05-Complete | John S.
2 - Medium | Richardson TX - EMI - Anechoic chamber: Engineering Labs Virtual Open House | Jeff Calloway--Brian Stapley and Mike Buscher |  | E36 | Video series |  |  |  | 40 |  |  | 05-Complete | John S.
2 - Medium | Richardson TX - F170 Electronics Lab: Engineering Labs Virtual Open House | Jeff Calloway--Brian Stapley and Mike Buscher |  | E36 | Video series |  |  |  | 40 |  |  | 05-Complete | John S.
2 - Medium | Richardson TX - Power Amplifier Lab (PA Lab): Engineering Labs Virtual Open House | Jeff Calloway--Brian Stapley and Mike Buscher |  | E36 | Video series |  |  |  | 40 |  |  | In-Review | John S.
2 - Medium | Richardson TX - Model Shop: Engineering Labs Virtual Open House | Jeff Calloway--Brian Stapley and Mike Buscher |  | E36 | Video series |  |  |  | 20 |  |  | In-Review | John S.
2 - Medium | Vergennes VT - Engineering Lab: Engineering Labs Virtual Open House | Jeff Calloway--Brian Stapley and Mike Buscher |  | E36 | Video series |  |  |  | 40 |  |  | Ready | Kevin & John
2 - Medium | Engineering Storage: Engineering Labs Virtual Open House | Jeff Calloway--Brian Stapley and Mike Buscher |  | E36 | Video series | 2022-05-04 | TBD |  | 40 |  |  | In process | John S.
2 - Medium | Vergennes VT - Environmental Lab: Engineering Labs Virtual Open House | Jeff Calloway--Brian Stapley and Mike Buscher |  | E36 | Video series | 2021-11-01 | TBD |  | 40 |  |  | In process | John S.
2 - Medium | Vergennes VT - EMI Area: Engineering Labs Virtual Open House | Jeff Calloway--Brian Stapley and Mike Buscher |  | E36 | Video series | 2021-11-01 | TBD |  | 40 |  |  | Complete | Kevin, John, & Mckenzie
2 - Medium | Embedded Computing Conference Recordings 2021 | Tara Kraft |  | Avionics Engineering Fellow - Corbett (000000261742) | Video series | 2022-12-01 | 2023-01-01 |  | 23 | 0 | 23 | In-Review | John S. | I am curious if you have bandwidth to help edit more of the Embedded Computing Conference recordings. We have all of the recordings from 2021 in this sharepoint: https://rtxusers.sharepoint.us/sites/GS-CAECC-COL I have not looked at them, but Matt said they need a lot of work. There are 6 days of recordings (I think close to 50 total). I'd be able to help provide information. Ideally we'd like to have them posted on the RTX video channel you created. It is not an immediate need, but I'd be curious if it is something you could help with over the next few months. You would be able to charge to Matt's fellows budget. (2023-07-20)
1 - High | Intelligent Gateway Product - Photos | Chad Bryant / Branden Setteland |  | GSBP2 KC-135 Prototypes STRATCOM B&P (000100142704 / 0452 / 0824) | Still Photography | 9/8/20223 | 2023-10-01 |  |  |  |  | 03-In process | John S. | Branden Sletteland brought in the product to shoot.
3 - Low | Safety 201 (complete but looking for distribution - may need scorm wrap) | Michael Peterson / Ann Yandell |  | FLIGHT CONTROLS FBW (XC2) | Video | ? | 2020-12-18 |  | ? |  |  | Waiting for more info | John S. | This project has been floating around for awhile since before both the aquasition and merger. Mike wants his videos to be put on the UTAS LMS (CATU), and Mary can't get access to the video files to check it out because of file size constraints, lack of know-how and lack of desire to check it out (she's busy etc.) Mike sent out an e-mail 9/3/20 to check with Mary about it - I'd be surprised if anything came of it. Project has now went to Ann Yandell (10/2/2020) -- The plan is to build out the course in "Bright Space" which links to the internal UTC LMS. Bright Space is a course authoring environment - it also hosts what is created in it. The neat thing about Bright Space is that you can make a course and have it show up in the LMS listings when people search for courses. | https://drive.google.com/drive/folders/1vN_qg8URItY2hp0-ZG4EI4qZ1-Sdcgqi
1 - High | FIT Annual Refresher | Scott Bradley |  | K00 | Traditional CBT | ? | ? |  | 40 |  |  | In process | John S. | Legacy RCU Work - (Ann/Paul) - Broken in current internal LMS - needs to be converted to HTML5. Same thing may need to be done to "WIN Labor Distribution Training" Sent Scott a video version of the course - waiting for feedback. If all is well, it will need to be sent to the enterprise LMS. https://crsvn.rockwellcollins.com/hr_cbt_projects_fy14/HR-course-FIT%20Labor%20Distribution%202020/trunk/Build/index.html Scott is ready to proceed on this using the example I sent over. Need to load it into the new internal LMS? | FY15 FIT Captivate files: http://crsvn.rockwellcollins.com/hr_isd_projects/FY15%20FIT/Design FY15 FIT PPT files: http://crsvn.rockwellcollins.com/hr_isd_projects/FY15%20FIT/Design
3 - Low | ESH New Hire Video | Adam Merritt |  |  | Video | [6 empty] | Bidding | TBD | Prob out of their price range...That's the vibe I got. Quoted 120 hours.
3 - Low | Traffic Aware Planner (TAP) | John Clemens |  |  | Traditional CBT | ? | ? |  | 80-120 |  |  | Waiting for more info | John S. | Bidding/Maybe pursuing - Internal ROM? Original content from NASA | https://drive.google.com/drive/folders/1z5WOViRcQb_OrZTkuebQlYWTI_E7KQTB

## Currently Available
GTS Courses Available for Registration - Successfactors - 10/13/2025
Course Type | P/N | Title
CBT | 5230825044 | Bombardier Challenger 604 Pro Line Fusion Avioncs System - Operator
CBT | 5230825045 | Bombardier Challenger 604 Pro Line Fusion Avioncs System - Maintenance
CBT | 5230824381 | Citation CJ Pro Line Fusion Operator
CBT | 5230824618 | Citation CJ Pro Line Fusion Maintenance
CBT | 5230808167 | Attitude Heading system (AHS-3000)
CBT | 5230808360 | Pro Line 4 - Learjet 60 Flight Line Maintenance
CBT | 523-0832124 | Essence Beverage Maker
CBT | 523-0832125 | Essence Espresso Maker
CBT | 523-0832126 | Essence Water Heater
CBT | 523-0833824 | Endura Water Heater
CBT | 523-0834910 | Endura DF/DS 3000 Oven
ILT | 523-0824946 | Bombardier Global 7500 Pro Line Fusion
ILT | 523-0836507 | Airshow HD
ILT | 523-0820277 | Pro Line Fusion A220
ILT | 523-0837076 | Venue Cabin Management with Audio Video Control Unit (AVCU)
ILT | 523-0824951 | Stage Maintenance Practices
ILT | 523-0825399 | Bombardier Challenger 604 Pro Line Fusion Maintenance
ILT | 523-0809440 | Tailwind 500/550
ILT | 523-0825401 | Bombardier Challenger 604 Pro Line Fusion Operator
ILT | 523-0824783 | Electronic Checklist Management Tool (ECMT)
ILT | 523-0809250 | Cessna Citation Pro Line 21 XLS+
ILT | 523-0824958 | Venue Innovative Cabin System (ICS)
ILT | 523-0821908 | Pro Line Fusion King Air
ILT | 523-0817473 | Pro Line Fusion Global 5000/6000

## Planned & In-Work
GTS Courses Migration In-Work - Successfactors
Course Type | P/N | Title | Target Date *subject to change
CBT | 5230808735 | Integrated Flight Information System (IFIS-5000) | <10/31/2025
CBT | 5230808822 | Flight Management System (FMS-3000) | <10/31/2025
CBT | 5230809379 | Pro Line 21 Hawker 800XP with IFIS | <10/31/2025
CBT | 5230809384 | Falcon 20/50 Pro Line 21 | <10/31/2025
CBT | 5230816899 | Pro Line 21 King Air 350 | <10/31/2025
CBT | 5230821912 | Pro Line fusion King Air - Pilot | <10/31/2025
CBT | 5230823320 | Pro Line fusion King Air - Flight Line Maintenance | <10/31/2025
CBT | 523-0832556 | Endura Beverage Maker ATLAS | <10/31/2025
CBT | 523-0832557 | Endura Beverage Maker ARINC | <10/31/2025
CBT | 523-0832834 | Modus Beverage Maker | <10/31/2025
CBT | 523-0832849 | Modus Water Heater | <10/31/2025
CBT | 523-0834224 | Essence DF/DS 3500 Oven | <10/31/2025
CBT | 5230833276 | Multiscan Recorded Training | <10/31/2025
CBT | 5230834416 | Multiscan Radar Training for Pilots - A220 | <10/31/2025