## Product Line - Part Move
Product Line or Part Move Checklist |  | Back To Index
|  | Supplier Self Risk Level Assessment | Low | Medium | High
Event Scenario:
You, the supplier, will be moving a product line or individual part to another facility location. Change may occur immediately or over time. The supplier must consider how the change will impact RC products and must ensure that the resources necessary for producing RC parts will be involved in the change.
Supplier Information:
Supplier Name:
Vendor Code:
Contact Name:
Contact Title:
Contact Phone:
Contact E-mail:
Primary RCI Buyer / SCM:
Risk Exposure:
Impacted Part Count:
Which open orders are impacted?
Please provide RC impacted parts list: (May attached parts list for easier consumption)
RC Sites [Potentially] Impacted | List
Items for Review: General Checklist
Provide impacted Rockwell Collins parts list
What is the date of move (how soon)?
What is the expected duration of the project?
Will any RC products be discontinued as a result of the move?
Will existing employees be relocating to the new facility? If not all, what percentage have accepted a transfer package?
Will the legacy facility be available as a backup if issues arise in the new facility? If so, how long to resume production?
Will equipment be moving or will new production equipment be purchased?
What is plan around transfer of WIP inventory and acquisition of raw materials?
Does the supplier have a knowledge transfer / succession plan in case of the exit of key personnel?
Who is your project manager and what is their contact information?
How often will we be cadenced on the project? (minimum weekly)
What is the lead time of the parts they provide (longest lead time parts are most critical)?
What are the most critical parts based on customer product delivery schedules?
What open orders are due around and following the move period (how many – how critical)?
Will the supplier build ahead quantities and maintain a finished goods buffer (overlap of supply between facilities)?
Equipment move - is critical production equipment being moved?
Special Tooling / Handling & Shipping of Tooling / Logging of Tooling
Who owns Tooling?
Does the move require CAE technical approval?
Is there opportunity or need for source inspection?
SCQA notified & SCQA move checklist completed if required (quality survey at new site if applicable)
Qualification of new site (RC 9000 applicable)
Should there be a site presence by RCI before or after the move?
Are there consignment Inventory buffers - should they be expanded?
Record retention / Quality Records, 3 yr retention & location (records of parts impacted, C of C, Plating, Heat Treating, Mfg processes etc)